Go Live - Post Game Analysis Template

This template is designed to capture the success and areas for improvements / learnings during the Build to Go-Live phase of the project implementation. The template consists of two questions that need to be answered by the respective cross-functional project team members. The Post Game Analysis (PGA) template is intended to be completed in a narrative style response.

To assist with writing the narrative, a series of reference questions are provided, but there is also room to add additional context and information as deemed necessary for each topic. The completed template will serve as the single source of information during a post-game discussion, which is expected to take place within two weeks of Go-Live.

It is recommended to make a copy of the template and save it here for further use

Project Information: (Filled by Svcs Ops)

| Solution Building block | Cl Client Name | Project Project Duration | Project Team Members |
| --- | --- | --- | --- |
| Financial Planning | R Resideo | Wave 1 - February 2023 – June 2024 Wave 2 - June 2024 - August 2024 | Tapan Mazumder - Delivery Director Ketul Kothari - Project Manager Shrikant Jadhav - Solution Architect Aniruddha Baskar - Config Lead Shashank Iyer - Functional consultant Rama Prabha - Functional consultant Sowmya Vishwanathan - Functional consultant Prashant Kumar - Integration architect Vignesha Varathan - Integration consultant Nikilesh Narayan - Functional consultant |

# Topic 1 - Plan Vs Actual (To be filled by PM and/or CM)

Wave 1 Information:

| Milestone | SOW start date (if one is present in SOW, if not use the project planned dates at the end of BP) | SOW end date (if one is present in SOW, if not use the project planned dates at the end of BP) | Actual Start date | Actual end date |
| --- | --- | --- | --- | --- |
| Build end | N/A | N/A | Feb 12th, 2024 | May 10th, 2024 |
| SIT end | N/A | N/A | May 13, 2024 | June 4th, 2024 |
| UAT end | N/A | N/A | June 3rd, 2024 | June 14th, 2024 |
| Go Live | N/A | N/A | June 24, 2024 | June 24, 2024 |

# Topic 2-  Build (To be filled by SA / Config Lead / Product Lead)

# What were the improvement opportunities during the build?

For Wave 1, we did not have a reference product, so we should have engaged into a more robust detailed design process including the usage of paper models. When we did not do that the first time around, we ran into issues with developing a solution that was fit-for-purpose. This translated into a need for a replanning phase where we re-baselined the project and engaged in redesign sessions inclusive of paper models. Wave 2 was a smaller scope, and we were able to start with the creation of a prototype for enhanced P&L/MOR reporting capabilities that was well received and thus led to the successful execution of Wave 2.

- What went well during the build?

When we worked on Wave 1 following the re-baseline, we held three validation cycles that helped the project team to give the client a demonstration of the built-out capabilities and validate them much earlier on in the build cycle. This allowed us to be able to compress the UAT timeline and ensure we were building functionality that was fit-for-purpose from the client’s perspective. From a project team perspective, we operated with 3 offshore configuration resources, 1 on-site technical lead, and 1 on-site functional lead. This served the project team well as the first time around we did not have a dedicated functional lead with expert knowledge of financial planning.

# Topic 3 - Quality (To be filled by CM and/or PM)

# What were the improvement opportunities in the overall testing process for the implementation?

We built both SIT and UAT test cases and developed those test cases ourselves instead of asking the Resideo team to help with the creation of those test scripts. While this allowed us to have better control over what would be tested during the testing cycles, I believe there may have been some less confusion related to the expected outcome of the test scripts if the client was more thoroughly engaged in the creation of the test cases. I also believe we should have developed a strategy for batch optimization activities prior to the cut-over/go-live in order to reduce some of the challenges with processing times that we faced with batch runs post go-live for Wave 1.

# Topic 4 - Data and Integration (To be filled by SA and/or IA)

# What were the improvement opportunities in terms of the data and integration?

Data & integration activities were completed quickly and timely. However, there could have been better communication on what errors were associated with source system data issues versus data conversion issues on the o9 side.

# Topic 5 - Environment (To be filled by SA / SS / Devops)

# What were the improvement opportunities in terms of the environment set up?

While environments were set up relatively quickly, we sometimes faced performance issues within the environments. This occurred primarily because of server size issues.

# Topic 6 - Change Management (To be filled by CM and/or SS)

# What were the improvement opportunities in terms of change management?

During the initial design validation phase for Wave 1, we should have solicited more detailed feedback from the end users upfront by pushing the client PMO team to ensure alignment with end users. This would have prevented the redesign sessions that needed to be completed during Q4 of 2023.

# Topic 7 - Client Relationship (To be filled by Sales Lead)

- What were the improvement opportunities in terms of establishing client relationships?

We have bi-weekly meetings with the client Resideo leadership team. This helps to provide them with status overviews and updates relating to the status of the implementation, any issues, roadblocks, and potential feedback. We also went to the client location on-site during may key pivotal portions of the implementation including blueprinting, validation cycles, UAT, and Go-live.

# Topic 8 - Value tracking (To be filled by CM / Sales Lead)

# Have we implemented value tracking during the implementation? Is it enabled on the o9 platform?

This is a non-reference model product. Financial Planning capabilities we have deployed for Resideo are also not on the product roadmap. Therefore, we do not have a value tracking setup in place.

Reference points for above questions (Think in terms of the following:-)

- Did we study the business case during the course of the implementation?

- Were we able to create a baseline at the beginning of the program?

- Is an ongoing measurement mechanism set up in o9 or outside?

- Has the client identified a value owner to drive the ongoing analysis and socialization?

- What are the challenges to achieving the value goals?

# Team feedback (Required)

Client Manager, Project Manager, SA/SS, IA, Config Lead, Sales Lead, Product leads provide peer feedback through Lattice (Use “Manager”or Private+Manager” visibility)

Dimensions to consider for feedback ( Not every dimension is applicable to every role):

- Knowledge (reference product, industry, domain)

- Configuration quality

- Sprint demo storytelling

- Proactively developing client relationships (users, program leadership, executive leadership)

- Scope management

- Program governance

This is not intended to be a detailed performance review (mid year or annual).

Screenshots below on how to provide feedback in Lattice: